# Rollout plan

Action list for the four-day week rollout. Page owner: Jamie Rivera. Last updated Friday, October 15, 2027. Fictional sample file for Microsoft Copilot Visual Bible, Book 4.

# Actions

| ID | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| A01 | Send written notice to Billing staff | Amara Okafor | 2027-05-10 | Done |
| A02 | Finance sign-off for the rollout budget | Kenji Watanabe | 2027-05-21 | Done |
| A03 | IT readiness checklist, Billing | Tomasz Kowalski | 2027-05-14 | Done |
| A04 | Send written notice to Dispatch staff | Amara Okafor | 2027-06-07 | Done |
| A05 | IT readiness checklist, Dispatch | Tomasz Kowalski | 2027-06-25 | Done |
| A06 | Put the 60-second review rule back in the plan | Sofia Martinez | 2027-05-14 | Done |
| A07 | Week 6 review, Billing | Jamie Rivera | 2027-08-16 | Done |
| A08 | Week 6 review, Dispatch | Jamie Rivera | 2027-09-13 | Done |
| A09 | 12-week review, Billing | Jamie Rivera | 2027-09-27 | Done |
| A10 | Confirm whether the Dispatch handsets are on the old supplier contract | Tomasz Kowalski | 2027-09-30 | Open |
| A11 | Agree month-end close cover for Billing | Sofia Martinez | 2027-10-08 | In progress |
| A12 | Update the FAQ for the customer letter | Amara Okafor | 2027-10-15 | Open |
| A13 | Get HR Director approval for the Dispatch two-group wording | Amara Okafor | 2027-10-22 | Open |
| A14 | 12-week review, Dispatch | Jamie Rivera | 2027-10-25 | Open |
| A15 | Tidy permissions on the project folder | Sofia Martinez | (none) | Open |
| A16 | Send Priya the quarterly cost summary | Kenji Watanabe | 2027-10-29 | Open |

Status is Open, In progress, or Done. Dates are written as year, month, day.