# Four-day week trial proposal

Prepared for the leadership team by the Customer Support team. October 2026. Fictional sample file for Microsoft Copilot Visual Bible, Book 2.

# Summary and decision requested

We ask the leadership team to approve a 12-week trial of a four-day work week for our customer support team of 12 people. The trial would start on Monday, January 4, 2027. During the trial, each person would work four 8-hour days on the same pay. The phone line would stay open from 8 AM to 6 PM, Monday to Friday, with at least 9 agents on duty at all times.

We need a decision by Monday, November 9, 2026, because our Working Hours Policy requires 8 weeks' written notice of a change. The trial also needs two written exceptions from the HR Director. At the end of the trial, we will report the results, including any that do not support the idea.

# Why we're proposing a trial

We surveyed all 12 people on the team. Eight are interested in a three-month trial: five are very interested and three are interested. Three are not sure, and one is not interested. Five people prefer four 8-hour days on the same pay, four prefer four 10-hour days, and three prefer to keep five days. The average satisfaction score for our current hours is 3.25 out of 5.

The team's biggest concern is customer waiting times, which four people named. Longer days, covering for absent colleagues, and pay and benefits were each named by two people.

Nobody knows yet what a four-day week would do to waiting times. A trial gives us real numbers for our own team, instead of opinions.

# How the trial would work

- Length. The trial would run for 12 weeks, from Monday, January 4, 2027 to Friday, March 26, 2027.

- Pattern. Four 8-hour days a week on the same pay. Four 10-hour days would break the policy's 9-hour limit on a working day (rule 3.3), so we are not proposing them.

- Cover. Twelve people working four days each gives about 9.6 people a day, which is only just above the minimum of 9. We would split the team into two groups, A and B, with different days off, so that nobody has the same day off as everyone else. Monday is our busiest day and Friday is the hardest day to cover, so the rota must be built around them.

- Opening hours. The phone line stays open from 8 AM to 6 PM, Monday to Friday.

The trial does not fit the policy as it stands. The table shows what we need for each rule.

| Policy rule | What it says | What the trial needs |
| --- | --- | --- |
| Rule 3.4 | Pay is reduced in proportion to hours worked. | Written approval from the HR Director to keep pay the same. |
| Rule 6.1 | Trials can last up to 8 weeks. | A written exception for a 12-week trial. |
| Rule 5.1 | A change needs 8 weeks' written notice. | Approval by Monday, November 9, 2026, so notice can be given in time. |
| Rule 4.2 | At least 9 agents must be on duty at all times. | No exception. The rota must meet this rule every day. |

# What it would cost and what could go wrong

We are not asking for extra staff, and pay would stay the same. We have not yet costed any cover or overtime that the rota might need, and Finance will want that figure before the trial starts.

The main risks are:

- Waiting times. Customer waiting times could get longer on Mondays, our busiest day.

- Satisfaction. Customer satisfaction could drop if the team is stretched.

- Fairness. Colleagues who prefer five days could feel pushed to cover for others.

- Contracts. Changes to working hours may affect contracts and employment terms, so HR must review the plan before anything changes.

# How we'll measure success

We will track four measures: average waiting time, answer rate, customer satisfaction score, and sick days. We will compare each one with a baseline from our call data for January to March 2026.

If the average waiting time goes above 60 seconds, we will stop and review the trial with the leadership team. We will check that 60 seconds is the right number before the trial starts.

We will report every result at the end, whether it supports the trial or not.

# Next steps

- Leadership team: decide by Monday, November 9, 2026.

- HR: review contracts, and give written approval for same pay and for a 12-week trial.

- Support team: build a rota with two groups and at least 9 agents on duty every day.

- Finance: cost any cover or overtime that the rota needs.

- Support team: give the team written notice by Monday, November 9, 2026, so the trial can start on January 4.