# Four-day week rollout plan: Billing and Dispatch

| Document detail |  |
| --- | --- |
| Version | 1.0 |
| Date | April 23, 2027 |
| Prepared by | Sofia Martinez, Operations |
| Sponsor | Priya Nair |
| Project lead | To be confirmed |
| Status | Draft for team comment |

# 1. Purpose and scope

Leadership has approved extending the four-day week to two more teams: Billing and Dispatch. This plan sets out how the rollout will work, when it will happen, and what it will cost. It builds on the 12-week trial run by the Customer Support team earlier this year.

Billing has 14 staff and Dispatch has 12 staff. Both teams start on Monday, July 5, 2027.

# 2. Working pattern

Both teams work four 8-hour days (32 hours a week) on the same pay. Friday is the non-working day for everyone in both teams. On Fridays, the Dispatch duty supervisor answers urgent calls, and Billing queries wait until Monday.

Same pay needs written approval from the HR Director under rule 3.4 of the Working Hours Policy.

# 3. Timeline and milestones

| Milestone | Billing | Dispatch | Proposed owner |
| --- | --- | --- | --- |
| Finance sign-off | June 1 | June 1 | Kenji Watanabe |
| Written notice to staff | May 24 | May 24 | Amara Okafor |
| IT readiness checklist | June 4 | June 4 | IT (to be confirmed) |
| Manager and team training | June 14 to 25 | June 14 to 25 | Sofia Martinez |
| Start of four-day week | July 5 | July 5 | Team leaders |
| Review after 12 weeks | September 27 | September 27 | Project lead |

The sponsor reviews each team's results 12 weeks after its start date.

# 4. Budget

| Item | Amount | What it covers |
| --- | --- | --- |
| Training | $12,000 | A half-day session for every team member and a one-day course for six team leaders |
| Scheduling software | $6,500 | Licenses for the rota tool for both teams |
| Temporary cover | $9,000 | Overtime for the first four weeks of each team's rollout |
| IT setup | $4,500 | Phone and rota tool setup for 10 phone seats |
| Communications and materials | $2,000 | Printed posters, a customer letter, and a staff guide |
| Total | $34,000 |  |

The plan assumes $12,000 for training, covering a half-day session for every team member and a one-day course for the six team leaders.

The total of $34,000 is within the $36,000 envelope set by Finance.

# 5. Roles

| Role | Name |
| --- | --- |
| Sponsor | Priya Nair |
| Project lead | To be confirmed |
| HR (policy, notices) | Amara Okafor |
| Finance (budget, sign-off) | Kenji Watanabe |
| Operations (plan, training) | Sofia Martinez |
| IT (phones, rota tool) | To be confirmed |

# 6. Risks and safeguards

- Phone cover: on Fridays the Dispatch duty supervisor answers urgent calls. If this proves too thin, the sponsor can change the arrangement.

- Review rule: if the average customer wait for a phone answer goes above 60 seconds for two weeks in a row, the sponsor calls a review within five working days.

- Customer awareness: printed posters in the Dispatch hall and a letter to key customers will explain the new Friday arrangements.

# 7. Open questions

- Will Finance approve the training figure?

- Who will be the project lead?

- How will Billing queries be handled on Fridays?